## Gantt Chart Template
IAJES GANTT CHART |  | Onlinegantt.com
| PROJECT TITLE | IAJES Website Redesign | COMPANY NAME |  | IAJES (International Association of Jesuit Engineering Schools)
| PROJECT MANAGER | Silvia Figuiera | DATE |  | Fall-Spring 2025-2026
|  |  | SUMMER |  |  |  | FALL | [9 empty] | WINTER | [9 empty] | SPRING
WBS NUMBER | TASK TITLE | PCT OF TASK COMPLETE | July | August |  | September | Week 1 Sept 21-27 | Week 2 Sept 28-Oct 4 | Week 3 Oct 5-11 | Week 4 Oct 12-18 | Week 5 Oct 19-25 | Week 6 Oct 26-Nov 1 | Week 7 Nov 2 - 8 | Week 8 Nov 9 - 15 | Week 9 Nov 16 - 22 | Week 10 Nov 30 - Dec 6 | Week 1 Jan 4 - 10 | Week 2 Jan 11 - 17 | Week 3 Jan 18 - 24 | Week 4 Jan 25 - 31 | Week 5 Feb 1 - 7 | Week 6 Feb 8 - 14 | Week 7 Feb 15 - 21 | Week 8 Feb 22 - 28 | Week 9 Mar 1 - 7 | Week 10 Mar 8 - 14 | Week 1 Mar 29 - Apr 4 | Week 2 Apr 5 - 11 | Week 3 Apr 12 - 18 | Week 4 Apr 19 - 25 | Week 5 Apr 26 - May 2 | Week 6 May 3 - 9 | Week 7 May 10 - 16 | Week 8 May 17 - 23 | Week 9 May 24 - 30 | Week 10 May 31 - Jun 6 | Week 11 Jun 7- 14
1 | Requirement Determination
1.1 | Review of Current Website | 100%
1.2 | IAJES Page Flowchart | 100%
1.3 | IAJES Website Proposal | 100%
2 | Figma & Design Development
2.1 | IAJES Figma Development | 75%
2.2 | IAJES Color Scheme Proposal | 100%
2.3 | New Logo Proposal | 100%
2.4 | IAJES Feature Priority Spreadsheet | 75%
2.5 | Layout and Color Brainstorm | 100%
2.51 | Visualizations 1-3 | 100%
2.52 | Final Visualiztion | 100%
3 | Initial Software Development
3.1 | Platform Determination | 25%
3.2 | Code Development | 0%
3.21 | Backend Training | 0%
3.3 | Code Review | 0%
4 | Software Development Finalization
4.1 | Code Development 2 | 0%
4.2 | Code Review 2 | 0%
5 | Release & Management
5.1 | Transfer of Ownership to IAJES | 0%
5.2 | Monitoring | 0%
5.3 | Bug Management / Website Upkeep | 0%
6 | Senior Design Requirements
6.1 | Senior Design Signature Page | 100%
6.2 | Funding Proposal Form | 100%
6.3 | Senior Design Thesis | 5%
6.4 | Conference Registration Form - Feb 1, 2026 | 0%
6.5 | Senior Design Conference - May 8, 2026 | 0%
6.6 | Senior Design Thesis Library Submission - June 11, 2026 | 0%