## Sheet1
ID | Priority | Effort | Feature | Description | Action | Page | Editing Capability
1.1 | High | High | Sign Up | Only allows university email. Allows task force admins, website managers, and superadmins access to various editing capabilities. Allows task force members access to their profile. | Sign up button to the signup page. Email text input and storage. Email verification send. Verification success & failure. Password text input and storage. Error handling for bad email/password input. (Captcha?) | All (header signup button), Signup | Regional representative, Website Manager
1.2 | High | Low | Login | Only allows university email. Allows task force admins, website managers, and superadmins access to various editing capabilities. Allows task force members access to their profile. | Login button to the login page. Email text input & validation. Password text input and validation. Error handling for bad email/password input. (Captcha?) | All (header login button) Login | Superadmin, Website Manager
1.3 | Medium | Low | Log Out | Allows users to securely end their session and clear login credentials from the system | Logout button to the logout confirmation page. Error handling on unsuccessful logout. | All (header logout button) | Superadmin
2 | High | Medium | Announcements | Updates IAJES members about important events and dates. | Add, start announcement from uploaded text file/PDF/document, delete, archive, unpublish, edit, save WIP, upload images & videos | Landing | Superadmin, Website Manager, Task Force Admin, Regional representative
3.1 | Medium | Medium | Newsletter Article Creation | Enables creation and editing of newsletter articles directly in the system, ensuring content can be drafted, revised and published efficiently | Create new, create from document upload, edit, save, publish | Newsletter | Superadmin, Website Manager, Task Force Admin, Regional representative
3.2 | Low | Medium | Newsletter PDF Generation | Generates a downloadable PDF version of the newsletter for archival or distribution purposes | Create PDF and automatic download, error handling if issues with generating PDF document | Newsletter | Website Manager
3.3 | High | Medium | Newsletter Email Blast | Sends the completed newsletter via email to subscribed emails (even non-IAJES) and mailing lists | Send email to mailing lists |  | Website Manager
4 | High | Low | Newsletter Subscription | Allows users to subscribe to receive newsletters and updates directly to their email |  | Landing | Superadmin
5 | Low | Low | Map | Displays an interactive map highlighting IAJES universities, member locations or event sites for easy visualization |  | Landing | Website Manager
6.1 | High | Medium | Add Task Force | Allows superadmins, website managers and task force admins to create new task force groups within the system, assigning names, detials and initial members | Add | Task Forces | Superadmin, Website Manager, Task Force Admin
6.2 | High | Medium | Edit Task Force | Enables modifications of existing task force information, including updating details, saving chnages and deleting task forces if needed | Edit, save, delete | Task Force | Superadmin, Website Manager, Task Force Admin
7.1 | Medium | Medium | Biannual Meetings Gallery | Provides funtionality to upload, edit and manage photos or media related to biannual IAJES meetings | Edit | Biannual Meetings | Superadmin, Website Manager, Task Force Admin, Regional representative
7.2 | Medium | Medium | Regional Meetings Gallery | Allows editing and management of photos or media specific to regional IAJES meetings | Edit | Regional Meetings | Superadmin, Website Manager, Task Force Admin, Regional representative
8.1 | Low | High | Search | Enables to users to search across members, task forces, and content throughout the platform to quickly find relevant information |  | All | Superadmin
8.2 | Low | High | Filter/sort | Lets users refine search results using filter and sorting options such as name, task force, industry, job/postion, country | Filter/sort options: name, task force, industry, job/position, country, major, research interest | Search | Superadmin
9.1 | High | Medium | User Profile | Shows and allows access to user information (why this task is not part of block 1?, related to the user sign/log in | Edit | User Profile | User
9.2 | Low | Medium | Contact | Sends an email to the user |  | User Profile | Website Manager, Task Force Admin, Regional representative
10 | High | High | Admin Roles | Grants authorized users the ability to assign or remove administrative roles from member profiles | Give and remove a profile's superadmin, website manager, or task force admin role. | Profile Page | Superadmin
|  |  | (maybe) IAJES Landing Page Highlights |  | Adding/editing/removing IAJES Landing page highlights | Landing page
|  |  | (maybe) Governing Board |  | Adding/editing/removing governing board members | Governing Board
|  |  | (maybe) Biennial Meetings |  | Adding/editing/removing biennial meetings | Biennial Meetings
|  |  | (maybe) Regional Meetings |  | Adding/editing/removing regional meetings | Regional Meetings
|  |  | (maybe) Contests |  | Adding/editing/removing contests | Contests
|  |  | (maybe) Research |  | Adding/editing/removing webinars | Webinars
|  |  | (maybe) Conferences |  | Adding/editing/removing conferences | Conferences
|  |  | (may be archived) Projects |  | Adding/editing/removing projects | Projects
|  |  | (may be archived) Webinars |  | Adding/editing/removing webinars | Webinars